## Sheet1
CiviHR_Bug001
Scope: | This document contains bug report for CiviHR.
Project Name | Civi HR - Recruitment portal
Module Name | CiviHR - Job Contract (Add and Edit)
Reported By | AK Systems Inc.
Reported To | CiviHR Development team
Reported On | 17/2/2017
Resolved by
Resolved On
Bug details
Bug ID | CiviHR_Bug001
Title | Add New Job Contract button should be disabled once it is clicked. Error message should be displayed only once.
Bug Description | Steps to reproduce : 1. Login as system admin and open Job contract page 2. Click on Add New Job Contract button, a popup form is displayed to add a new contract. 3. Insert valid data in all fields and click on Add New Job Contract button more than once. System displays error messages more than once. Button should be disabled once it is clicked. Same issue is there for all the buttons.
Status | Open
Severity | Major
Classification | Functional issue
Is it Reproducible | Always
Snapshots | CiviHR_001.jpg
CiviHR_Bug002
Scope: | This document contains bug report for CiviHR.
Project Name | Civi HR - Recruitment portal
Module Name | CiviHR - Job Contract (Add and Edit)
Reported By | AK Systems Inc.
Reported To | CiviHR Development team
Reported On | 17/2/2017
Resolved by
Resolved On
Bug details
Bug ID | CiviHR_Bug002
Title | Replace html of Choose files button with html of Add new job contract button. System takes invalid entries without any validation.
Bug Description | Steps to reproduce : 1. Login as system admin and open Job contract page 2. Click on Add New Job Contract button, a popup form is displayed to add a new contract. 3. Insert valid data in all fields. 4. Open inspect element and copy the html code of Add new job contract button. 5. Replace the html code of browse button with this Add new job contract button code. 6. Now, replace valid data with invalid data in all/any fields. Eg. End date should be less than start date (Start date - 01/02/2017 and End date - 01/08/2015) 7. Click on Add new job contract button placed at browse button. System accepts invalid data without checking any validation. Client side and server side validations both should be there for each form.
Status | Open
Severity | Critical
Classification | Security issue
Is it Reproducible | Always
Snapshots | CiviHR_002.jpg ; CiviHR_003.jpg ; CiviHR_004.jpg
CiviHR_Bug003
Scope: | This document contains bug report for CiviHR.
Project Name | Civi HR - Recruitment portal
Module Name | CiviHR - Job Contract (Add and Edit)
Reported By | AK Systems Inc.
Reported To | CiviHR Development team
Reported On | 17/2/2017
Resolved by
Resolved On
Bug details
Bug ID | CiviHR_Bug003
Title | Job contract should reflect immediately when added.
Bug Description | Steps to reproduce : 1. Login as system admin and open Job contract page 2. Add new job contract with valid data in all fields. 3. Check the contract on Contract list page. Newly added Contract should be displayed in list of contract page immediately. Here it is displayed on page refresh. 4. Open Add Job Role form 5. Check the new added contract in Contract dropdown Newly added Contract should be dispalyed in Contract dropdown on Job role form. Here it is displayed on page refresh.
Status | Open
Severity | Major
Classification | Functional issue
Is it Reproducible | Always
Snapshots | CiviHR_005.jpg ; CiviHR_006.jpg ; CiviHR_007.jpg